## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Secret Design | Completed | 5
Project title | Setshabelo Admission System | In Progress | 0
Stakeholder or organisation | Setshabelo Primary School | Not Started | 0
Group mentor | Mr Elton Mokoduwe | Delayed | 0
Reporting phase | Phase 3 | Blocked | 0
Reporting period | 28/09/2026 - 30/10/2026 | Overdue | 0
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Setting up Supabase as our database and intergrating both platforms (Flutter & ASP.Net) to use the same database. | Contribution entries | 9
Main challenge | Our main challenge was getting our mobile app (user side) to intergrate with Supabase. We managed fix the problem. | Verified entries | 9
Next planned activity | To demonstrate that our prototype works perfectly on both the user side (Flutter) and admin side (ASP.net) using Supabase as a shared database.. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U4-01 | Phase 3 | Activity 4.1 | Set up and implement shared Supabase backend | Lebohang Molise | 28/10/2026 | 05/10/2026 | Completed | 100 |  | Yes |  | Completed
U4-02 | Phase 3 | Activity 4.2 | Develop Flutter application | Relebohile Thito, Tshepo M Masimong, Njabulo R.A. Mthethwa | 06/10/2026 | 13/10/2026 | Completed | 100 |  | Yes |  | Completed
U4-03 | Phase 3 | Activity 4.3 | Develop ASP.Net application | Lebohang Molise, Andries M Matona, Lonwabo Sifuba | 06/10/2026 | 13/10/2026 | Completed | 100 |  | Yes |  | Completed
U4-04 | Phase 3 | Activity 4.4 | Integrate Flutter and ASP.Net with Supabase | Lebohang Molise | 14/10/2026 | 16/10/2026 | Completed | 100 |  | Yes |  | Completed
U5-01 | Phase 3 | Activity 5 | Prototype completion and manual testing | Whole group | 19/10/2026 | 23/10/2026 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Lebohang Molise | 224078106 | Phase 3 | Setting up and integrate Supabase | Set up Supabase as our database and integrated both Flutter and ASP.Net with Supabase | Assigned Resonsibility | 2026-10-05 | 72 | https://supabase.com/dashboard/project/hrkzdekzmqjiejjuwybh/editor/25507?schema=public | Yes | 06/10/2026
Relebohile Thito | 221027701 | Phase 3 | Develop and Test Flutter application | Worked on project configuration, models class, profile screen, application form with steps screen and parent dashboard screen | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Flutter-Mobile-Application | Yes | 14/10/2026
Tshepo M Masimong | 223081118 | Phase 3 | Develop and Test Flutter application | Worked on view models, school achievements screen, my application details screen and applications screen | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Flutter-Mobile-Application | Yes | 14/10/2026
Njabulo R.A. Mthethwa | 221032310 | Phase 3 | Develop and Test Flutter application | Worked on the supabase services part of the mobile application, login screen, register screen and update screen | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Flutter-Mobile-Application | Yes | 14/10/2026
Lebohang Molise | 224078106 | Phase 3 | Develop and Test ASP.NET application | Worked on project configugation, controllers and services. Worked on the admin side of the web application | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Website-Application | Yes | 14/10/2026
Andries M Matona | 221021198 | Phase 3 | Develeop and Test ASP.NET application | Worked on the views of the web application for it to have similar look to the mobile application | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Website-Application | Yes | 14/10/2026
Lonwabo Sifumba | 220049798 | Phase 3 | Develop and Test ASP.NET application | Worked with Andries on the look of the web application and worked on the viewmodels | Assigned Resonsibility | 2026-10-13 | 144 | https://github.com/WIL-Project-Hub/Setshabelo-Integrated-Website-Application | Yes | 14/10/2026
Lebohang Molise | 224078106 | Phase 3 | Integrate Supabase with Flutter and ASP.NET | Connected the web and mobile application with the backend | Assigned Resonsibility | 16/10/2026 | 72 |  | Yes | 19/10/2026
Whole Group |  | Phase 3 | Prototype completion and manual testing | Manually tested the application on both both platforms for errors and to see if it works perfectly | Assigned Resonsibility | 2026-10-23 | 120 |  | Yes | 21/10/2026

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
22/10/2026 | Phase 3 | Site Visit | Demonstrate prototype to stakeholder and get feedback. | Whole Group | Mr F.M kgomoaleburu | The prototype works perfectly on both mobile (Flutter) and web (web version). The stakeholder was very pleased with our work and the prototype | There is no further action required | Signed confirmation document found on the SRS

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
14/10/2026 | Phase 3 | Capturing user information on mobile app | We had to fix this issue before moving on to other aspects of the development | A change was made to one one of the methods used | Relebohile Thito | 16/10/2026 | Resolved
14/10/2026 | Phase 3 | Integrating Flutter with Supabase | The error caused us to fix the issue before moving on to other tests | The correct API Key was used to connect Flutter and Supabase | Lebohang Molise | 16/10/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 3 | Initial or updated SRS completed | Yes
Reporting period | 30/10/2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Develpoment of the prototype. Integrating both Flutter and ASP.net to the same database (Supabase). Completion of prototype. Manual testing and fixing of errors in prototype | Stakeholder engagement recorded | Yes
What remains incomplete? | N/A | Challenges and actions updated | Yes
Why is it incomplete? | N/A | Group reflection completed | Yes
Which contributions were particularly important? | All development elements in this phase because they are all interdependent for the prototype to work perfectly and as intended | Microsoft Project updated | Yes
Were there participation concerns? | No, every member contributed equally in this phase | GitHub evidence available | Yes
What will the group improve in the next phase? | This is the final phase of the system | Confidential peer check completed | Yes
Main priority for the next phase | N/A

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 3 | Length | Approximately 300–400 words in total.
Project title | Setshabelo Admission System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Development and manual testing of prototype | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Developing the prototype: As a group we were already familiar with Flutter and ASP.net. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Integrating the prototype to Supabase especially on the mobile app (Flutter): We made a mistake of API Keys as we were coding the prototype. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | We divided ourselves into two groups of three people: Relebohile Thito, Tshepo M Masimong and Njabulo R.A. Mthethwa were assigned to wotk on the mobile app (Flutter). Lebohang Molise, Lonwabo Sifumba and Andries M Matona were assigned to work on the web version (ASP.Net). Integration to Supabase was done by the whole group
Did all members contribute fairly? Explain. | Yes all mambers contributed fairly, all members worked on their tasks diligently and we all helped each other if ever a group member was having a problem with their particular task in the develpoment of the prototype
How did the group handle disagreements or delays? | We helped each other whenever there were delays, on conflicts we tried by all means to resolve them as soon as possible so that we can finish the prototype in the specified time we had
What did the group learn from the stakeholder? | The stakeholder was pleased with the prototype demonstrated and how easy it was to use
Improvement action 1 for the next phase | N/A
Improvement action 2 for the next phase | N/A
Priority for the next phase | N/A